## Sheet1
Frontend (HTML + Dynamic)
Pages Name | Section | Time (in Hours) | Notes
Home | Banner section | 2 | At this time, we are estimate this time with 6-7 sections such as the - Banner section, - About section, - Services-related section (if the brand offers any), - FAQ section, - Newsletter section, - Blog listing section, and - Social media post display section - along with Header and Footer. If there is any additional section outside of these and challenging design, we will provide a separate time estimate for it based on the design.
| About section | 2
| Services-related section (if the brand offers any) | 3
| FAQ section | 2
| Newsletter section | 1
| Blog listing section | 3
| Social media post display section | 2
| Header with Normal menu | 4 | We will provide a basic header that will be fully responsive on every screen.
| Header with Mega Menu | 8 | However, if the header design is more complex, such as incorporating mega menus, additional time will be required for that, and we will provide a separate time estimate.
| Footer | 3
Inner Page | Not more than 3-4 Sections | 14 | We will develop an inner page, such as the About page. If the modules are similar to the homepage and only one or two sections are different, we will include that in this development. However, if all the sections on the page are different, we will provide a separate time estimate for it. For the website, if all the pages have the same modules, it will take us 8 hours per page to develop.
Blog Listing | Not more than 3-4 Sections | 8 | We will provide a blog listing page, which will also include single blog posts. If there are any filters or search functionality on the blog listing page, the time estimate will increase, and we will provide a separate time estimate for that.
Single Blog Page |  | 8
Contact | A basic contact form with no other integrations will be provided. | 5 | On the contact page, we will include a form along with its integration, such as saving form entries in the admin panel and sending them to the admin via email. Additionally, we will add a map section and an address section. If the design includes more sections on the contact page and need to integrate with something like - Google Sheets, - Mailchimp, - Salesforce, then an additional time estimate will be provided for that.
| Google Sheet Integration | 3
| Mail Chimp Integration | 4
Search |  | 4 | We will be implementing a search functionality on the website, including a search option in the header and creating search results pages in a grid format, similar to the blog listing page. By default, the search will be limited to blog posts only. If you require the option to search other types of content, such as pages, custom posts, or other data, we will provide an additional time estimate for that.
E-Commerce
If the website is eCommerce, here are the default pages we provide along with their time estimates:
Pages Name |  | Time (in Hours) | Notes
Product |  | 8 | We will provide a products listing page in a grid format. If the design deviates from the grid layout, we will provide a separate time estimate based on those requirements.
Register |  | 4 | This includes the basic design, as well as the complete functionality for login and registration. For the reset password functionality, we will provide the email-based feature where the user will need to enter their email or username, and a reset password link will be sent to their email.
Login
Reset Password |  | 1
Dashboard |  | 1 | In the user dashboard, we will provide the these default pages with a basic design, aligned with the brand's color scheme/theme. However, if you want to add any additional pages or make design changes to the user dashboard, we will provide an estimate based on those requirements.
Orders |  | 3
Downloads |  | 1
Addresses |  | 2
Payment methods |  | 4
Account details |  | 3
Cart |  | 4
Checkout |  | 5
Emails |  | Time (in Hours) | Notes
New order |  | 4 | We will provide all these emails by default, with a basic design according to the brand's color scheme/theme. If you need any additional emails beyond these, we will provide a separate time estimate for them.
Cancelled order
Failed order
Processing order
Completed order
Order details
Reset password
New account
Admin Dashboard
Post Types |  | Time (in Hours) | Notes
Wordpress Installation |  | 0.5
Theme Creation |  | 5
Post |  |  | These are the default post types in WordPress, and we will use them to create pages/posts on the front end. There will be no additional time required for this; the time estimate for creating any page/post has already been provided above.
Pages
Menu Creations | Normal menu | 1
| Mega Menu | 3
Website Security | Wordfence Plugin / All in one Security | 3 | We will install and properly set up a security plugin for the website to prevent malware attacks." Additionally, we will ensure that the plugin is configured to provide comprehensive protection, including regular malware scanning, firewall protection, and blocking suspicious activity. Keeping the security features updated will be a priority to maintain ongoing protection against potential vulnerabilities and threats.
Spam Protection | Google Captcha Integration | 0.5 | We will set up Google Captcha on the website to ensure spam protection." In addition to this, we will configure it to reduce automated bot attacks, ensuring that only legitimate users can access forms and other entry points on the site. Combining Google Captcha with other security measures like regular plugin updates and backups will strengthen the overall security of the website.
CPT | Only for 1 post type | 15-20 | If we need a custom post type other than the blog, we will create a custom post type for it. Additionally, we will need to display it on the front end, which involves creating the HTML and making it dynamic. For all of this, a separate time estimate will be required, and it will take at least 15-20 hours to complete.
If the website is eCommerce, here are the default option we provide in admin panel along with their time estimates:
Product |  | 10 min per product | There is a default option to add products, which includes fields for the product name, description, feature image, categories, variations, tags, pricing, and stock management. No additional time is required for these standard options. However, if the client wants any custom options beyond what is mentioned, we will provide an additional time estimate based on the specific requirements.There is a default option to add products, which includes fields for the - product name, - description, - feature image, - categories, - variations, - tags, - pricing, - and stock management. No additional time is required for these standard options. However, if the client wants any custom options beyond what is mentioned, we will provide an additional time estimate based on the specific requirements.
Payment Gateways |  | 2 | We can set up - Cash on Delivery (COD), - Stripe as payment gateways. If there is any request for a new payment gateway integration, we will provide an additional time estimate for the implementation.
Shipping |  | 2 | By default, using WooCommerce, products can be shipped to all countries. If you want to add a filter to limit shipping to specific locations, areas, or zip codes, this can be set up without any additional time. However, if we need to research and find the regions or zip codes according to the locations, and this information is not provided by the client, it will require extra effort. In such a case, we will provide an additional time estimate.
Server Setup
Instance Creation |  | 1
DNS Integration |  | 1
SSL Setup |  | 1
SMTP Creation |  | 1
Securing Database |  | 1

## Sheet2
Home | 15 | At this time, we are estimate this time with 6-7 sections such as the If there is any additional section outside of these and challenging design, we will provide a separate time estimate for it based on the design.
|  | - Banner section, | 2
|  | - About section, | 2
|  | - Services-related section (if the brand offers any), | 2
|  | - FAQ section, | 2
|  | - Newsletter section, | 2
|  | - Blog listing section, and | 2
|  | - Social media post display section | 2
|  | - along with Header and Footer. | 2